Project Charter

·  Version 1.0  ·  Third Wave Inc.

Required fields must be completed before stakeholder sign-off.

☆ Optional fields are recommended but not mandatory.

| Project Name | Ontokb-E Enterprise Platform Transformation – Subteam 2 |
| --- | --- |
| Project Manager | Zhang Dapeng — Third Wave Inc. |
| Project Leader (Tech Lead) | Pooja — Third Wave Inc. |
| Sponsor / Stakeholder | ______________________ — Third Wave Inc. |
| Document Number | TW-ONT-2026-002 |
| Version | 1.0 |
| Created Date | 2026-10-14 |
| Last Updated | 2026-10-14 |
| Status | Proposal (Under Review) |

0.  Revision History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | 2026-10-14 | Project Team (Subteam 2) | Initial project proposal |

1.  Project Overview

Guide What is this project about? Keep this short — 2 to 3 sentences. Answer: what will be built, who benefits, and what problem does it solve? Avoid technical jargon.

| Purpose | Transform LOGOS/OntoKb from a single-purpose customer-support reply assistant into a domain-neutral enterprise platform, so that any business domain can be onboarded through configuration, with enterprise-grade security, governance and scalability. |
| --- | --- |
| Background / Problem | LOGOS was originally built for one use case: drafting Dospara customer-support replies. Its business rules are embedded in the core services, its data model (ontology) is not enforced at runtime, and key enterprise capabilities such as multi-tenancy, enforced authentication, separation of duties, tamper-evident audit and horizontal scaling are not yet in place. These limitations prevent the platform from being used in other business domains. |
| Expected Benefit | New business domains onboarded through configuration, without changes to core services. Related documents linked automatically, even when they are received weeks apart. All services authenticated; every business action checked against policy and audited. Multiple instances per service, with verified data isolation between tenants. |
| Project Type | Enhancement (re-architecture of the existing LOGOS/OntoKb platform) |

2.  Scope

Guide Clearly state what IS and IS NOT included in this project. Being explicit about what is out of scope prevents disputes later.

| In Scope | Enterprise ontology redesign: shared core data model with versioning, enforced object lifecycles (state machines) and time-aware actions (validity windows, deadlines, approval expiry). Domain-neutral platform: customer-support and meeting-specific modules replaced by configurable domain packs. Cross-document relationship detection: automatic linking of related documents received at different times, with timelines and change tracking. Knowledge and retrieval layer redesigned to serve any content type under release control. Workflow orchestration, data pipeline and runtime performance improvements. Agent and model layer: provider-independent model gateway, prompt management and AI safety controls. Control plane and Workbench redesign with single sign-on and role-based access. Enterprise security and governance: authentication on all services, multi-tenancy, separation of duties, tamper-evident audit and data protection. Operational readiness: horizontally scalable services, monitoring, CI/CD and automated testing. |
| --- | --- |
| Out of Scope | Changes to the PostgreSQL database (schemas, tables, indexes or version). Usage metering, billing and formal compliance certification (planned for a later phase). Migration of historical customer-support data. Mobile applications and rollout to external customer environments. |
| Assumptions | The solution approach is agreed before development starts. The current technology stack is retained: Node.js 22, TypeScript, PostgreSQL 16, OpenSearch and S3-compatible storage. Team members have access to the source repository and a shared development environment. A test identity provider and AI model API access are available to the team. |
| Constraints | Development effort: 80 person-hours across a team of three (Subteam 2). Development labour is internal and not charged; project budget ¥27,500 (excluding tax). All project data is confidential and remains within Third Wave Inc. |

3.  Schedule Overview

Guide Enter the major phases and their target dates. The full Gantt chart and WBS are in the Project Plan (). This section is the high-level timeline the stakeholder approves.

| Phase | Owner(s) | Effort (person-hours) | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1: Detailed Design & Environment Setup | Tech Lead, Developer, QA Engineer | 10 | Module-level technical design, development environment and CI pipeline, test plan. |
| Phase 2: Development – Core Platform | Tech Lead, Developer | 22 | Enterprise ontology with state and action engine, domain packs, identity, multi-tenancy, approvals and audit. |
| Phase 3: Development – Platform Capabilities | Tech Lead, Developer | 22 | Cross-document relationship detection, knowledge retrieval, orchestration, agent and model layer, control plane. |
| Phase 4: Testing & UAT | QA Engineer, with developer support | 20 | Functional, security, multi-tenancy and performance testing; defect fixing; UAT support. |
| Phase 5: Release & Handover | Tech Lead, Developer, QA Engineer | 6 | Release preparation, technical documentation, handover and closure report. |
| Total | Development team (3) | 80 |  |

4.  Budget Overview

Guide Enter the total budget and main cost categories. Detailed tracking is in the Budget Tracking Sheet (). The stakeholder approves the total here.

| Cost Category | Budget (¥, excl. tax) | Notes |
| --- | --- | --- |
| Development Labor | ¥0 | Internal team — no outsourcing (80 person-hours across 3 members) |
| Infrastructure / Cloud | ¥10,000 | One small cloud test server; local development on existing machines |
| Licenses & Tools | ¥15,000 | Open-source stack with no licence fees; AI model API usage for testing |
| Other Expenses | ¥0 | No travel or external services |
| Contingency | ¥2,500 | 10% risk buffer on non-labor direct expenses |
| TOTAL | ¥27,500 | Excluding tax |

5.  Project Team

| Role | Name | Department | Responsibility |
| --- | --- | --- | --- |
| Stakeholder / Sponsor | ______________________ | Third Wave Inc. | Final approval, budget, business decisions |
| Project Manager | Zhang Dapeng | Third Wave Inc. | Overall delivery, schedule, risk, stakeholder reporting |
| Project Leader (Tech Lead) | Pooja | Third Wave Inc. | Architecture, technical decisions, development, code review (30 h) |
| Core Developer | Jaiadithya | Third Wave Inc. | Core platform development, action runtime, ontology engine, unit testing (30 h) |
| QA Engineer | Balachandra | Third Wave Inc. | Test planning, test execution, benchmark evaluation, defect management (20 h) |

6.  Key Risks

Guide List the top risks anticipated at project start. Full risk tracking is in the Project Management Log () Issue & Risk Log.

| # | Risk | Impact | Probability | Response |
| --- | --- | --- | --- | --- |
| 1 | Development effort exceeds the 80 person-hour estimate | High | Low | Prioritise foundation work, track effort weekly, and manage changes via Change Request Form; defer lower-priority items. |
| 2 | Replacing customer-support modules disrupts existing functions | Medium | Medium | Introduce domain-pack structure first and maintain automated tests before removing legacy modules. |
| 3 | AI relationship-detection and extraction accuracy below target | Medium | Medium | Human review of low-confidence results; evaluation dataset checked before each release. |

7.  Success Criteria

Guide Measurable criteria for declaring the project a success. Vague criteria cause disputes — be specific with numbers. These feed directly into the UAT Sign-off ().

| # | Criterion | Target | Measurement |
| --- | --- | --- | --- |
| 1 | All features pass User Acceptance Testing (UAT) | 100% pass rate | UAT Sign-off |
| 2 | Enterprise security baseline at release | All services authenticated; 0 Critical vulnerabilities | Security Test Report |
| 3 | A new business domain is onboarded through configuration | No changes to core service code | Demonstration and code review |
| 4 | Related documents are linked across time | ≥ 85% precision on evaluation dataset | Evaluation Report |

8.  Approval

The signatories below confirm that they have reviewed this Project Charter and authorise the project to commence. Scope, budget, and timeline are agreed as stated above.

| Role | Name | Date | Signature / Seal |
| --- | --- | --- | --- |
| Stakeholder / Sponsor | ______________________ | 2026-10-14 | Pending approval |
| Project Manager | Zhang Dapeng | 2026-10-14 | Pending approval |
| Project Leader (Tech Lead) | Pooja | 2026-10-14 | Pending approval |

cy against your actual project details.